 Industrial Project
 Reflective Journal
 TOM GORA
 B01665261
Module: WRKB10001 - WBL 4 – Industrial Project
Year: 2025
Term: 1 and 2
Coordinator: Tom Caira
Project Org: Lochwinnoch Community Development Trust
 Contacts
@ TRUST’S WEBPAGE
@ COORDINATOR’S LINKEDIN
@ STUDENT’S PORTFOLIO
01

---
 Table of Contents
Project Overview
03
Reflection on Prior Academic Learning
05
Reflection on the Development and Application of Work in Client Environment
06
Initial Planning and Backend Selection Challenges
06
Planning and Deployment Challenges
07
Security Incident and Learning
08
Technical Integration Issues
09
Reflection on Personal and Professional Development
10
Reflection on Technical and Learning Skills Achieved
11
Technical Skills Development
11
Changed Perspectives on Professional Practice
12
Areas for Further Development
13
Reflection on Future Career
13
Tangible Outcomes and Portfolio Development
14
Skill Alignment with Industry Demands
14
Adaptability and Breadth of Skill in the Modern Market
14
Solidifying Career Direction
15
Summary
16
Client Feedback
16
Overall Professionalism Discussion
17
Bibliography
18
Appendices
19
02

---
 Project Overview
The industrial project undertaken focused on the complete redesign and development of
a new website for the Lochwinnoch Community Development Trust (LCDT). LCDT is a
non-profit organization established 12 years ago to build local community and realize
various related projects in this village in the historic west central area of Scotland. With
over 300 members, the project presented an ideal balance for an academic industrial
placement—larger in scope and impact than a small sole trader website, yet still
manageable for a student developer working independently.
This project presented a unique opportunity to work outside traditional corporate
constraints. The relatively small scope afforded considerable freedom to explore,
create, and learn while implementing modern web development practices. However, this
freedom came paired with the significant responsibility of delivering a polished,
professional product that could be effectively managed by organizational
representatives with minimal technical knowledge. This balance between creative
autonomy and practical implementation for non-technical end-users became a central
consideration throughout the development process.
The previous LCDT website had several limitations that hindered its effectiveness as a
community resource and organizational tool. An initial analysis revealed opportunities
for improvement in terms of design, functionality, content management, and
accessibility. The organization required a digital platform that would effectively represent
its mission while enabling non-technical staff to maintain and update content
independently.
03

---
Based on this analysis, the project objectives were defined as follows:
1. Design and develop a modern, visually appealing website that appropriately
represented LCDT and its community activities
2. Implement a content management system (CMS) that non-technical staff could
easily use to update content
3. Ensure high accessibility standards to serve the diverse community members
4. Create a cost-effective solution that would be sustainable for a small non-profit
organization
5. Deliver a minimum viable product (MVP) with core functionality while allowing for
future enhancements
The project was successfully completed with the delivery of a fully functional MVP
website that met all the primary objectives. Key achievements include:
1. Development of a responsive website built using Astro as the frontend framework,
chosen for its performance benefits and modern development capabilities
2. Implementation of Directus as a headless CMS, providing an intuitive interface for
content editors with different permission levels
3. Creation of four theme variants, including high-contrast AMOLED options
specifically designed for accessibility
4. Integration of various accessibility features including ARIA attributes, semantic
HTML, skip navigation buttons, and adjustable font size and contrast settings
5. Deployment of the solution on a Virtual Private Server (VPS) using Docker,
resulting in a cost-effective hosting arrangement at approximately £5 per month
6. Establishment of role-based access control, allowing administrators and editors
different levels of system access appropriate to their responsibilities
7. Implementation of a streamlined content workflow where editors can create, edit,
publish, and unpublish content with immediate frontend reflection
While some planned features such as comment functionality and tag-based
organization were deferred to post-MVP development phases, the delivered website
provides LCDT with a solid foundation that meets their immediate needs while allowing
for future expansion and refinement based on user feedback and organizational
requirements.
04

---
 Reflection on Prior Academic Learning
My educational journey in software development began at college with fundamental
programming concepts taught through Java console applications and introductory PHP
websites. This was later expanded at university with additional exposure to more PHP
echo statements plus Java in the form Android “Hello World”, and Microsoft Java in the
form of C#. Joking aside, while these experiences established important foundational
knowledge, the LCDT website project required a substantially different approach and
technology stack that better aligned with current industry practices.
The transition from structured academic assignments to this real-world project
highlighted both the benefits and limitations of traditional coursework. While university
modules introduced important theoretical concepts around responsive design and
accessibility standards, they often remained anchored to technologies and approaches
that felt disconnected from contemporary development practices. This industrial project
provided a refreshing opportunity to break free from curriculum constraints and explore
more modern frameworks and methodologies that would deliver greater value to the
client.
However, this project also revealed significant opportunities for growth beyond the
academic curriculum. The decision to use Astro as a frontend framework and Directus
as a headless CMS represented a deliberate departure from more conventional
academic technologies like PHP-based content management systems. This choice
stemmed from extensive self-directed learning in my personal time, where I’ve explored
contemporary development tools including various JavaScript frameworks, Linux
customization, and automated workflows that streamline development processes.
My self-initiated exploration of modern development ecosystems proved invaluable
when confronted with the practical challenges of the LCDT project. The coursework-
based understanding of software development lifecycles provided structure, but
implementing a solution that prioritized both user accessibility and administrative
simplicity required drawing on knowledge acquired through independent study and
experimentation. This balance between academic foundations and self-directed learning
ultimately enabled a more innovative approach than might have been possible following
strictly academic methodologies.
05

---
The most significant realization during this project was recognizing that academic
coursework often prioritizes conceptual understanding over practical implementation.
While university assignments frequently focus on isolated technical problems with
predetermined parameters, the LCDT website demanded consideration of competing
priorities: technical excellence, client needs, user accessibility, and long-term
maintainability. This holistic perspective required synthesizing knowledge across
multiple domains rather than applying single concepts in isolation.
Perhaps most importantly, this industrial project provided space to apply my natural
inclination toward problem-solving and technical exploration in a structured context with
tangible deliverables. Where academic assignments sometimes felt disconnected from
industry realities, this project offered a meaningful bridge to professional practice. The
experience reinforced that while formal education establishes important fundamentals,
the rapidly evolving nature of web development demands continuous self-education and
adaptation beyond the curriculum—a reality that has shaped my approach to
professional development and career planning moving forward.
 Reflection on the Development and Application of Work in Client
Environment
 Initial planning and Backend Selection Challenges
A fundamental early decision involved determining the core technology stack,
particularly concerning the Content Management System. Given the client’s existing
familiarity with WordPress, continuing with that platform was an initial consideration.
However, the period during which these decisions were being made (late 2024)
coincided with significant turbulence within the WordPress ecosystem. Widely
publicised legal disputes involving major stakeholders, concerns regarding project
governance, and debates about the platform’s technical direction contributed to a
prevailing sentiment of instability among segments of the developer community.
Coupled with long-standing criticisms regarding WordPress’s perceived architectural
complexity, performance limitations for certain use cases, and the potential overhead
associated with its plugin-heavy ecosystem, these factors prompted a careful re-
evaluation.
06

---
Considering the project’s goal to deliver a lean, modern, maintainable, and user-friendly
solution for non-technical administrators, and viewing this industrial project as a key
opportunity for exploring contemporary best practices, I decided against rebuilding
within the WordPress framework. Instead, I undertook research into alternative, self-
hostable CMS solutions that might better align with the project’s specific requirements.
Several options were evaluated: TinaCMS was considered for its innovative live-editing
capabilities directly on the rendered page, but its being a relatively new project, lack of
documentation maturity, heavy React dependency destroying any simplicity of chosen
framework (much more than selective “interactive islands approach of Astro”), and
setup complexity were potential drawbacks. PayloadCMS offered significant flexibility
and a “code-first” approach, appealing for customization, but appeared to require
substantial configuration effort from a bare-bones base and seemed heavily oriented
towards Next.js and automated deployments like Vercel, which were not part of this
project’s stack. Strapi, which I had prior experience with, was also evaluated, but its
administrative interface, while powerful, felt potentially too technical in its abstraction of
database concepts and vocabulary for the intended non-technical end-users at LCDT.
Ultimately, Directus was selected. Its modern user interface, comprehensive out-of-the-
box features (user roles, content modeling, API generation), and the perceived ease
with which administrators could configure and manage content without deep technical
intervention made it the most suitable choice for balancing developer flexibility with end-
user simplicity for this specific project context.
 Planning and Deployment Challenges
When starting this project, I promised to deploy a demo myself where client could check
it out and play around with. This decision forced me to seriously learn Docker,
understand images, containers and all the surrounding context as my previous
knowledge was basic if not very limited. Before this, my approach in college was just
placing static sites in a directory to serve, and for applications just running them via
systemd service and telling Apache to proxy. I knew my existing server setup for
portfolio where I would deploy the demo was a mess and not adequate, with setup done
years ago when I was just blindly copying recipes from Stack Overflow to make things
work while learning.
07

---
This need to improve deployments coincided with requirements from another module -
Server Side Systems. I was having issues there because I could not deploy the old way.
I developed at home on Fedora with PHP 8.3 while the server was on stable Debian
with older incompatible version of PHP. I tried manual upgrading outside of package
manager but made mess. I broke existing setup and ended with version conflicts, tried
downgrading (which as I learned is something that is borderline impossible to do with
PHP) and then literally killed my Apache setup by tweaking configs.
This is where I decided time to learn properly and all my public facing projects would
benefit from this stepping up. I cmpletely deleted everything from the old days - Apache,
broken PHP versions, messy directories in
, simply everything I had. I set
 /var/www/
up new organized structure in /srv/ with proper organization for apps, backend, sites
and dedicated directory for industrial project demo.
To optimize rebuilding effort I chose Caddy, modern server written in Go which is great
because it comes with automatic SSL cert setup, has config that is pleasant to write and
simple (miles ahead of Apache), and excellent documentation. As I learned Docker
properly I found package called
 which is comprehensive TUI for managing
 lazydocker
docker, sparing me time exclusively using commands. I tidied everything and ultimately
this sidequest gave me completely new robust portfolio where all projects are
dockerized, securely exposed to localhost and sitting behind reverse proxy with fail2ban
and ufw properly configured for security.
 Security Incident and Learning
Big challenge that caused my significant concern was learning the important lesson to
NOT expose Docker containers directly and put everything behind proxy and firewall.
After deployment I noticed slowness but initially thought it was due to using the most
affordable VPS option. This was not the case. After few weeks, an alert email from
Linode prompted me to investigate. The server was operating at 100% CPU usage
continuously due to a cryptominer infection.
08

---
I spent an entire weekend troubleshooting before understanding what was happening.
The mining application was located in
 directory and masqueraded as a kernel
 /tmp
worker process. I became quite alarmed when I observed “kworker” consuming all
available resources. After terminating the process and removing related components, it
would reappear within minutes, again utilizing 100% CPU. Online research suggested a
possible rootkit infection requiring complete server replacement. When I discovered my
personal computer also showed “kworker” processes, my concern intensified
considerably.
The actual issue was that I had inadvertently left a PostgreSQL port exposed to the
internet, thinking I would connect from a local GUI application. This was a critical
mistake. With an open port, automated bots can quickly gain access, install mining
software, and name it to resemble legitimate system processes. I removed the
malicious software, but legitimate kworker processes appearing in the process list were
actually normal system routines. I nearly proceeded with completely replacing the
server – even purchasing a new virtual machine. Fortunately, I reconsidered, conducted
proper research, and implemented appropriate server hardening measures. The server
continued to receive numerous connection attempts for some time, but eventually these
subsided as the automated botnet attempts timed out.
 Technical Integration Issues
Another significant challenge that considerably impacted my progress for a week
occurred when components that functioned correctly in development failed in
production. On the server, the Directus container was unable to start the service,
generating a
 error in the stack trace. I conducted extensive
 TypeError: fetch failed
investigation following GitHub issues and research threads, configuring various
container settings, and attempting different network configurations including Docker
network, external network, and localhost, all without success. The solution eventually
came through advice from community members on Directus’ Discord support forum,
who suggested running the container in host mode to force localhost communication
without port mapping and Docker DNS. The underlying issue appears to be in the undici
HTTP client for Node.js, as similar symptoms are documented in GitHub issues. For a
small website behind a reverse proxy, utilizing host network mode was an acceptable
compromise.
09

---
The final issue was more straightforward but somewhat embarrassing – I had not
properly considered the implications of incorporating React for client-side rendering.
During the initial presentation with the module coordinator, the application functioned
correctly on my development machine where Directus was running locally. However,
when the coordinator accessed the site through their browser, the client-side JavaScript
attempted to connect to localhost on their machine where no endpoints existed. The
solution required replacing localhost references with the actual domain in URL
configurations. Fortunately, I had stored URLs in an
 file, requiring changes in
 .env
only one location. This experience reinforced the importance of proper project
configuration and demonstrated the value of centralized configuration through
 .env
files and CSS variables as implementations of the single source of truth principle.
Despite these challenges, a structured approach to development and willingness to
learn new technologies led to successful delivery of a functional, accessible website
meeting LCDT’s primary objectives. The journey reinforced that adaptability and
continuous learning are essential qualities in software development projects.
 Reflection on Personal and Professional Development
This industrial project significantly developed my professional capabilities and
understanding of ethical practice in ways aligning with British Computer Society (BCS)
Code of Conduct core principles.There are four of them listed on the official webpage of
BCS:
The BCS principle “You make IT for everyone” directly informed my approach to
accessibility. Rather than treating accessibility as an optional enhancement, I
implemented high-contrast themes, semantic HTML, ARIA attributes, and adjustable
display settings as core requirements. This commitment to inclusive design reflects the
professional responsibility to ensure technology serves diverse user needs.
“Show what you know, learn what you don’t” became particularly relevant when
confronting deployment challenges. Recognizing my limited Docker experience, I
deliberately chose to expand my capabilities rather than relying on familiar but less
optimal solutions. This principle guided my response to the security incident as well -
rather than resorting to a complete server replacement, I invested time in properly
understanding the root cause and implementing appropriate security measures.
10

---
The principle “Respect the organisation or individual you work for” manifested in my
collaborative approach with LCDT. By maintaining transparent communication about
technical challenges and ensuring the final product aligned with their specific
organizational needs, I demonstrated respect for their mission and requirements.
“Keep IT real. Keep IT professional. Pass IT on” influenced my approach to security
hardening following the cryptominer incident. This experience reinforced that
professional integrity involves not only addressing immediate issues but also preventing
deployed systems from becoming vectors for malicious activity that could impact others.
The lessons learned during this project - particularly regarding deployment security and
configuration management - represent valuable knowledge I can apply to future projects
and share with colleagues.
 Reflection on Technical and Learning Skills Achieved
This industrial project significantly expanded my technical capabilities across multiple
domains while providing valuable insights into areas for future development. The
experience transformed my understanding of modern deployment practices and
reinforced the importance of security, configuration management, and systems
integration.
 Technical Skills Development
The most substantial technical growth occurred in containerization and deployment
automation. Prior to this project, my deployment experience was limited to conventional
approaches using direct file placement and server configuration. Implementing Docker
containerization required developing an entirely new skill set, including understanding
container lifecycles, networking, volume management, and orchestration.
This expansion of capabilities extended beyond the immediate project requirements,
creating valuable transferable skills applicable across diverse technology stacks. I
applied these newly acquired skills to containerize various applications including
Laravel, PHP, React, multiple CMS systems, and even Spring Boot projects as I
migrated my previous work to the new infrastructure.
11

---
Server security represented another area of significant technical development. The
cryptomining incident provided practical experience in threat detection, system
hardening, and security best practices. Learning to implement and configure tools like
 and UFW (Uncomplicated Firewall) established essential skills for
 fail2ban
responsible systems administration. This experience transformed my approach to
deployment security from reactive to proactive, emphasizing preventative measures
rather than incident response.
Integration challenges between Astro and Directus developed technical problem-solving
skills, particularly in diagnosing complex system interactions. The experience reinforced
the importance of understanding network topologies in containerized environments and
the distinctions between different communication methods (Docker networks, host
networking, port mapping). This knowledge proved especially valuable when
troubleshooting production environment issues that did not manifest during
development.
 Changed Perspectives on Professional Practice
This project fundamentally altered my perception of configuration management and
environment variables. Previously, I had primarily used
 files exclusively for
 .env
storing sensitive information like credentials. The experience of managing environment-
specific configuration demonstrated the broader utility of centralized configuration
beyond merely protecting sensitive information. This represents a significant evolution
in my understanding of software architecture best practices.
Similarly, the deployment security incident transformed my approach to system
exposure and the principle of least privilege. The experience reinforced that proper
security is not merely about responding to known threats but about minimizing attack
surfaces through deliberate access restrictions. This represents a shift from a feature-
centric development mindset to one that incorporates security considerations
throughout the development lifecycle.
12

---
 Areas for Further Development
While the project substantially expanded my technical capabilities, it also highlighted
several areas for continued professional development:
1. Container Orchestration: While I successfully implemented basic
containerization, more complex orchestration tools like Kubernetes remain an area
for future exploration, particularly for larger deployments requiring automated
scaling and high availability.
2. Automated Testing: The URL configuration issue that emerged during
demonstration might have been detected earlier with more comprehensive testing
practices, suggesting an opportunity to develop stronger automated testing skills.
3. Infrastructure as Code: Although the deployment environment was successfully
established, the process relied partially on manual configuration. Implementing
infrastructure as code approaches would enhance reproducibility and disaster
recovery capabilities.
4. Frontend Performance Optimization: While accessibility features were
successfully implemented, further optimization of client-side performance would
enhance user experience, particularly for users with lower-bandwidth connections.
This industrial project ultimately transformed my self-perception from a primarily
development-focused practitioner to a more holistic technologist capable of addressing
the complete application lifecycle from requirements through secure deployment and
maintenance. This broader perspective has significant implications for future
professional opportunities and specialization directions.
 Reflection on Future Career
This industrial project has provided not only significant technical learning but also
valuable clarity regarding future career aspirations and professional positioning within
the software development landscape. The practical experience gained, particularly in
navigating the full project lifecycle from requirements gathering through to deployment
and security hardening, has substantially shaped my perspective on desirable roles and
necessary skill sets in the current industry.
13

---
 Tangible Outcomes and Portfolio Development
The primary tangible outcome, the redesigned website for the LLL Community
Development Trust, serves as a concrete demonstration of applied skills. There exists
potential to continue collaboration with the client beyond the scope of this academic
module, further developing the platform based on their evolving needs. Should this not
materialise, the project itself provides a robust, real-world example suitable for
rebranding and inclusion in my professional portfolio. In today’s competitive job market,
presenting such a comprehensive project – encompassing modern frontend
development with Astro, headless CMS integration using Directus, containerized
deployment via Docker, and security considerations – is significantly more impactful
than theoretical exercises or smaller code snippets. It showcases the ability to deliver a
complete, functional product.
 Skill Alignment with Industry Demands
The specific technical challenges encountered during this project directly fostered skills
highly relevant to contemporary industry demands. The deep dive into Docker for
containerization and Caddy for modern web serving and proxying, necessitated by the
deployment requirements and issues with older methods, provided practical DevOps
experience. Similarly, confronting and resolving the server security incident offered
invaluable, albeit stressful, lessons in system hardening, firewall configuration (ufw,
fail2ban), and the critical importance of secure deployment practices – skills often
sought after in roles beyond pure development. The focus on accessibility throughout
the design and implementation phase also aligns with the growing industry emphasis on
inclusive design and regulatory compliance.
 Adaptability and Breadth of Skill in the Modern Market
Undertaking this project as the sole developer required a breadth of involvement across
various domains – requirements analysis, technology selection, frontend design
(adapting a theme), backend integration (CMS), deployment, and security. This
experience underscored the value of adaptability and a holistic understanding of the
development process. In an era where AI tools are increasingly capable of handling
routine coding tasks, the ability to learn quickly, integrate diverse technologies,
troubleshoot complex issues (like the undici bug or the localhost configuration error),
and manage the entire lifecycle becomes a key differentiator.
14

---
This project provides strong evidence of that adaptability and a willingness to tackle
challenges across the stack, positioning me not just as a coder in one niche, but as a
versatile developer capable of contributing more broadly, which I believe is increasingly
necessary for career longevity and success.
 Solidifying Career Direction
While this project provided a valuable opportunity to engage with a modern technology
stack (Astro, exploring CMS options on the market) and contemporary practices like
containerization, it is understood that professional software development frequently
involves navigating different realities. Much industry work centres on maintaining legacy
codebases, integrating with existing systems, operating within corporate constraints, or
competing with established solutions like WordPress templates. This industrial project,
therefore, stands out not necessarily as a direct template for all future work, but as a
significant opportunity within the academic framework to freely explore technologies
beyond the standard curriculum. Successfully delivering the project under these
conditions demonstrated a crucial capacity for self-directed learning, adaptability in
choosing and integrating appropriate tools for the job (like selecting to use and learn
Caddy for simplicity that involved some learning but produced lean and configurable
setup to save time in the end), and resilience in overcoming unforeseen technical
challenges. These are transferable professional attributes valuable irrespective of the
specific technological environment encountered in future roles, showcasing an open-
minded approach and a readiness to learn and adapt – qualities essential for navigating
the complexities of real-world software engineering.
15

---
 Summary
This reflective journal detailed a range of experiences from initial project planning
through final deployment. Several key moments and challenges significantly shaped
both the final product and my personal growth. The development journey of the LLL
Community Development Trust (LCDT) website emphasized careful planning, security
and importance of learning new concepts. Overall that made an interesting and
impactful course.
A core element that requires analysis is feedback from the client at the time of
submission.
 Client Feedback Analysis
The LCDT provided several points about the final result. First, there needs to be some
cleaning in design to enhance user engagement. Currently design and usability feels
basic as the minimalistic look requires improvement and in general breaking blocks of
text will improve readability as it can feel too large. There are suggestions of
standardising font sizes and headers to create cohesive look and enhancing engaging
visuals. They stated need to work on improving content as key objectives for supporting
trust need to be more prominent and to simplify navigation journey for finding support.
Website need more obvious cues for contact submissions and other common questions
to improve user engagement. With better description implemented website can provide
clear and more easy understanding about objectives. There also seems to be some
need for improvements in meta descriptions to improve search visibility. Some elements
of the website do have good contrast but it is important to improve it. Finally there is
some need for clearity with action cues as they are currently understated, and that
privacy policy should also be standardised and more transparent. For them transition
with more user friendly CMS will be useful.
These critiques can be interpreted with a mix of reactions both validating the effort done
and showing potential for new improvements in future versioning, while it can be looked
for in both ways they are at the time for me extremely useful points for understanding
the product by those to whom it is dedicated and their needs. This has highlighted
important communication considerations in project and requirements gathering to make
a client engaged in active way to provide more information.
16

---
 Overall Professionalism Discussion
These problems that occurred highlight the importance of clear communication. While
the end outcome was successfull, there has been times while working on the project on
client’s lack of feedback I found in many ways myself unsure what course to take. If
these problems are there it is extremely likely to see them again.
I understand this is often caused by external circumstances like this in this case, I need
to understand that time management and engagement often is hard task to enforce in
certain external context, my goal is in the future to create some strategy to work in
those situations even with smaller or non-existent timeframe and with almost 0 external
inputs, as at that point my professional qualities, knowledge and experience has to
shine.
I approached development and deployment with consistent effort to meet the project
goals in the specified time frame, which while hard I consider as a skill to try to push
and improve whenever the change happens. If I plan on making this the focus of my job
search from here, these points can serve as basis for personal roadmap. I also need to
make sure that I keep improving my communications in every direction, as again, the
skill matters. This requires further engagement with industry and to better structure the
time, focus and to look for assistance whenever required.
Even with several challenges that were present the project succeeded for two reasons,
that on planning step all main project goals have had clear expectations how they are
made and that willingness to solve new problems I had for the entire journey. That
makes clear and measurable what it is supposed to be achieved and solve at those
constraints but at the same time do the thing for real and not just repeat recipes. In
future it will require more communication with team and customer and better
understanding of the domain. There can be new interesting areas of software industry
to consider moving forward.
This experience reinforced how professional competence directly links to public interest
and well-being. With that mindset and the lessons extracted this far, this project has laid
a strong foundation for my future professional and personal development.
17

---
 Bibliography
Astro. (2025). Dante | Astro. [online] Available at: https://astro.build/themes/details/dante/ [Accessed 2 Apr.
2025].
Docs. (2025). Getting started. [online] Available at: https://docs.astro.build/en/getting-started/ [Accessed 2
Apr. 2025].
Youtube.com. (2025). Available at: https://www.youtube.com/watch?v=XoIHKO6AkoM [Accessed 2 Apr.
2025].
Docs. (2025). On-demand rendering. [online] Available at: https://docs.astro.build/en/guides/on-demand-
rendering/ [Accessed 2 Apr. 2025].
Docs. (2025). @astrojs/react. [online] Available at: https://docs.astro.build/en/guides/integrations-guide/react/
[Accessed 2 Apr. 2025].
Docs. (2025). @astrojs/node. [online] Available at: https://docs.astro.build/en/guides/integrations-guide/node/
[Accessed 2 Apr. 2025].
Docs. (2025). Build your Astro site with Docker. [online] Available at: https://docs.astro.build/en/recipes/
docker/ [Accessed 2 Apr. 2025].
Directus Docs. (2025). Fetch Data From Directus with Astro | Directus Docs. [online] Available at: https://
directus.io/docs/tutorials/getting-started/fetch-data-from-directus-with-astro [Accessed 2 Apr. 2025].
Directus Docs. (2025). Overview | Directus Docs. [online] Available at: https://docs.directus.io/self-hosted/
docker-guide.html [Accessed 2 Apr. 2025].
Docker.com. (2025). Available at: https://hub.docker.com/r/directus/directus [Accessed 2 Apr. 2025].
Matheson, B. (2021). How to Permanently Kill and Remove kdevtmpfsi or kinsing - brycematheson.io. [online]
brycematheson.io. Available at: https://brycematheson.io/how-to-permanently-kill-and-remove-kdevtmpfsi-
kinsing/ [Accessed 2 Apr. 2025].
docker-library (2021). kdevtmpfsi virus use 99% of cpu · Issue #1127 · docker-library/php. [online] GitHub.
Available at: https://github.com/docker-library/php/issues/1127 [Accessed 2 Apr. 2025].
nodejs (2023). TypeError: fetch failed · Issue #1248 · nodejs/undici. [online] GitHub. Available at: https://
github.com/nodejs/undici/issues/1248 [Accessed 2 Apr. 2025].
nodejs (2024). fetch times out in under 5 seconds · Issue #1531 · nodejs/undici. [online] GitHub. Available at:
https://github.com/nodejs/undici/issues/1531 [Accessed 2 Apr. 2025].
18

---
 Bibliography
Astro. (2025). Dante | Astro. [online] Available at: https://astro.build/themes/details/dante/ [Accessed 2 Apr.
2025].
Docs. (2025). Getting started. [online] Available at: https://docs.astro.build/en/getting-started/ [Accessed 2
Apr. 2025].
Youtube.com. (2025). Available at: https://www.youtube.com/watch?v=XoIHKO6AkoM [Accessed 2 Apr.
2025].
Docs. (2025). On-demand rendering. [online] Available at: https://docs.astro.build/en/guides/on-demand-
rendering/ [Accessed 2 Apr. 2025].
Docs. (2025). @astrojs/react. [online] Available at: https://docs.astro.build/en/guides/integrations-guide/react/
[Accessed 2 Apr. 2025].
Docs. (2025). @astrojs/node. [online] Available at: https://docs.astro.build/en/guides/integrations-guide/node/
[Accessed 2 Apr. 2025].
Docs. (2025). Build your Astro site with Docker. [online] Available at: https://docs.astro.build/en/recipes/
docker/ [Accessed 2 Apr. 2025].
Directus Docs. (2025). Fetch Data From Directus with Astro | Directus Docs. [online] Available at: https://
directus.io/docs/tutorials/getting-started/fetch-data-from-directus-with-astro [Accessed 2 Apr. 2025].
Directus Docs. (2025). Overview | Directus Docs. [online] Available at: https://docs.directus.io/self-hosted/
docker-guide.html [Accessed 2 Apr. 2025].
Docker.com. (2025). Available at: https://hub.docker.com/r/directus/directus [Accessed 2 Apr. 2025].
Matheson, B. (2021). How to Permanently Kill and Remove kdevtmpfsi or kinsing - brycematheson.io. [online]
brycematheson.io. Available at: https://brycematheson.io/how-to-permanently-kill-and-remove-kdevtmpfsi-
kinsing/ [Accessed 2 Apr. 2025].
docker-library (2021). kdevtmpfsi virus use 99% of cpu · Issue #1127 · docker-library/php. [online] GitHub.
Available at: https://github.com/docker-library/php/issues/1127 [Accessed 2 Apr. 2025].
nodejs (2023). TypeError: fetch failed · Issue #1248 · nodejs/undici. [online] GitHub. Available at: https://
github.com/nodejs/undici/issues/1248 [Accessed 2 Apr. 2025].
nodejs (2024). fetch times out in under 5 seconds · Issue #1531 · nodejs/undici. [online] GitHub. Available at:
https://github.com/nodejs/undici/issues/1531 [Accessed 2 Apr. 2025].
18

---
 Appendices
 Appendix 1
[source code]
GITHUB LINK
 Appendix 2
[critique feedback from the client]
19

---
Overall Summary
The website has a clean, minimalistic look but requires improvements in design, usability, and content
management to enhance user engagement and accessibility. Key recommendations include optimising visual
appeal, organising content clearly, and ensuring mobile compatibility. Addressing these areas will strengthen
the Trust’s outreach efforts and encourage greater community support.
Design & Usability
The design is currently functional but minimalistic, making it less visually appealing. To enhance user
engagement, consider breaking up large blocks of text with images or varied layouts. Standardising headers
and font sizes throughout the site will create a cohesive look. Additionally, improving the quality of images
and expanding the use of engaging visuals, such as an immersive header image, will enrich the overall user
experience.
Content Quality
Content organisation needs improvement; key objectives and reasons for supporting the Trust should be
more prominent on the homepage. Consider user journeys by simplifying navigation to make it easier to find
relevant information. Information about becoming a member should be more accessible, ideally placed on the
‘Support Us’ page. Including an impact statement and a clearer outline of the Trust’s mission will strengthen
communication with potential supporters.
Functionality
While the site loads quickly on both desktop and mobile devices, there are broken links that need attention,
such as the ‘Go Fund Me’ link and some missing images. Contact forms would benefit from clearer prompts
and visual cues, such as asterisks for required fields, to improve user engagement. Additionally, ensuring error
messages are displayed in real-time rather than after submission will enhance usability.
SEO
To improve search visibility, it is essential to incorporate relevant keywords throughout the website.
Implementing meta descriptions for all pages will aid both user understanding and search engine indexing.
Furthermore, adding alt text for images, ensuring the site is optimised for mobile, and embedding a Google map
will improve local SEO rankings and enhance user experience.
Accessibility
The site currently has some good contrast between text and background, but larger blocks of text can be
overwhelming. A more distinct hierarchy of headings will enhance navigation and readability. It is vital to provide
alt text for images and consider additional multimedia content, such as video, to cater to users who prefer visual
information. Ensuring that text sizes are accessible and easy to read is crucial for inclusivity.
Audience Engagement
Calls to action, like signing up for newsletters or getting involved, should be more visible and user-friendly.
Incorporating share buttons on projects and news sections will encourage greater interaction. A dedicated
‘Support Us’ section should streamline the process for users wishing to engage with the Trust, making it easier
for them to take action.
Security and Compliance
The privacy policy needs standardization across different sections of the site, written in clear and plain language
for better user understanding. Including compliance checkboxes for sign-up forms is necessary to ensure GDPR
compliance and protect users’ personal information.
Management of CMS
While Directus can be an effective CMS, its complexity may pose challenges for our team who have limited
technical expertise. A transition to a more user-friendly platform may be beneficial for easier maintenance and
regular updates, ensuring we can efficiently manage and edit content without needing extensive coding skills.
18